## Sheet1
Project Development Flow
| Step |  | Primary Task |  | Parallel Task |  | Parallel Task
| 1 |  |  | Develop required SQL statements
| 2 |  |  | port Car.java from starter code
(replace id with vin)
| 3 |  |  | Implement CarDAO.java
| 4 |  | A | Design UI (includes defining naming all controls) | B | Design UI (includes defining naming all controls)
|  |  |  | CarlotView.java |  | AddVehicleView.java
| 5 |  | A | Implement UI functionality | B | Implement UI functionality | C | Style UI with application.css
|  |  |  | CarlotFX.java |  | AddVehicleFX.java
Step 5C is optional. At that point the project will be fully functional ▲
Completed
Needs Testing
In progress
| Task | Persons Involved
Completed | 1 | Andy Short
Completed | 2 | Andy Short
Needs Testing | 3 | Andy Short
4A
4B
5A
5B
5C